## Dashboard
Turin Mobility AI — Project Progress Dashboard
Metric | Value | Progress Metric | Value
Total Tasks | 21 | Overall Progress | 90.48%
Completed | 19 | Milestones Done | 6
In Progress | 0 | Days Logged | 3
Blocked | 0
Day | Average Progress %
1 | 100
2 | 100
3 | 100
4 | 50
5 | 15
6 | 100
7 | 100
8 | 100
9 | 100
10 | 100
How to use: Update Status, Progress %, Notes and Daily Log every day. The Dashboard updates automatically.

## Project Plan
Turin Mobility AI — 10-Day Project Plan
Day | Date | Phase | Task | Deliverable | Status | Progress % | Notes / Issues | Evidence / File
1 | 2026-09-09 | Data | Download Traffic and Parking data | traffic.xml and parking.xml | Done | 100 | Official 5T real-time feeds | data/raw/
1 | 2026-09-09 | Data | Inspect XML structure | Fields and record structure understood | Done | 100 | Traffic: 112 records; Parking: 41 records | notebooks/01_data_inspection.ipynb
2 | 2026-09-10 | Data | Check missing values and duplicates | Data quality checks | Done | 100 | Parking has 4 missing values in free; all have status 0 | notebooks/01_data_inspection.ipynb
2 | 2026-09-10 | Data | Convert numeric columns to correct data types | Clean Pandas DataFrames | Done | 100 | convert trafic and parking from object to float and int | notebooks/02_data_cleaning.ipynb
3 | 2026-09-11 | Database | Design PostgreSQL tables and relationships | Database schema | Done | 100 | primary keys in traffic we have different offset but both positive for sensor-i so we consider sensor-id+direction+offset as primary key | paparking_locations,parkinion observation
3 | 2026-09-11 | Database | Load cleaned data into PostgreSQL | Working PostgreSQL database | Done | 100 |  | creat csv parking?clean ,traficcc dlean , parking observation and traffice observation
4 | 2026-09-12 | Analysis | Write SQL analysis queries | SQL analysis file | Done | 100 |  | sql/03_analysis_queries.sql
4 | 2026-09-12 | Analysis | Perform Python EDA | EDA notebook and charts | Not Started | 0 |  | notebooks/03_exploratory_analysis.ipynb
5 | 2026-09-13 | BI | Build a small Power BI dashboard | 1-page mobility dashboard | Not Started | 0 |  | powerbi/dashboard.pbix
5 | 2026-09-13 | RAG | Collect official ZTL and parking documents | Official document set | Done | 100 |  | documents/official/
6 | 2026-09-14 | RAG | Clean and chunk documents | Prepared text chunks | Done | 100 |  | src/rag/ingest.py
6 | 2026-09-14 | RAG | Create embeddings and vector database | Persistent Chroma database | Done | 100 |  | src/rag/
7 | 2026-09-15 | RAG | Build retrieval function | Working RAG prototype | Done | 100 |  | src/rag/retriever.py
7 | 2026-09-15 | RAG | Add source citations | Grounded answers with sources | Done | 100 |  | src/rag/retriever.py
8 | 2026-09-16 | Agent | Create Data Analysis tool | Working data tool | Done | 100 |  | src/agent/tools.py
8 | 2026-09-16 | Agent | Create RAG tool | Working RAG tool | Done | 100 |  | src/agent/tools.py
9 | 2026-09-17 | Agent | Build agent routing | Agent chooses correct tool | Done | 100 |  | src/agent/agent.py
9 | 2026-09-17 | Agent | Test multi-tool questions | Combined Data + RAG answers | Done | 100 |  | evaluation/
10 | 2026-09-18 | App | Build Streamlit interface | Working application | Done | 100 |  | app.py
10 | 2026-09-18 | Evaluation | Evaluate 20 questions | Evaluation results | Done | 100 |  | evaluation/results.csv
10 | 2026-09-18 | Delivery | Finalize README, and GitHub | Portfolio-ready repository | Done | 100 |  | README.md / Dockerfile

## Daily Log
Daily Work Log — Update This Every Day
Day | Date | What I Completed Today | Problems / Blockers | What I Learned | Next Step | Time Spent (hrs) | Daily Status | library that I installed in this projects | write code in sql
1 | 2026-09-09 | Downloaded and inspected the official Turin Traffic and Parking datasets.Traffic: 112 records.Parking: 41 records.Checked columns, missing values and duplicate records |  | Learned how to read XML data with Python, inspect XML attributes, convert XML records into Pandas DataFrames, and perform basic data quality checks. |  |  | Done
2 | 2026-09-10 | convert data type from trafic and parking to float and int |  | I used FOR for changing object to int and float in trafic and for parking I used pd.tonumeric and FOR here python autpmatocally understand which of them must change to float which of them change to int in parking we have missing value it is better use it |  | 2 hours | Done |  | SELECT
3 | 2026-09-12 | make tabel make relation in posgersql and convert clean data from python to postersql |  | collected_at = pd.Timestamp.now() for making timestep we need for making trafica and parking observation 2- making csv file for traffic and parking after cleaning data change xml to csv43- make tabel in posteger for paring and traffic make quary -5convert data from python to table parking and traffic |  | 2 hours | Done |  | WHERE
4 | 2026-09-12 | 1-write 10question for parking and traffuc2-for 7 days want to collect data in Windows Task Scheduler |  |  |  |  | Not Started |  | ORDER BY
5 | 2026-09-13 | [5 empty] | Not Started |  | COUNT
6 | 2026-09-14 | [5 empty] | Not Started |  | SUM
7 | 2026-09-15 | [5 empty] | Not Started |  | AVG
8 | 2026-09-16 | [5 empty] | Not Started |  | IS NULL
9 | 2026-09-17 | [5 empty] | Not Started |  | GROUP BY
10 | 2026-09-18 | finish project |  |  |  |  | Not Started |  | calculated columns

## Milestones
Project Milestones Milestone یعنی یک نقطه مهم تحویل
Milestone | Target Day | Target Date | Success Criteria | Status | Notes
M1 — Raw Data Ready | 1 | 2026-09-09 | Traffic and Parking XML downloaded and inspected | Done
M2 — Clean Data Ready | 2 | 2026-09-10 | Data quality checked and numeric columns converted | Done
M3 — PostgreSQL Database Ready | 3 | 2026-09-11 | Tables, relationships and data load completed | Done
M4 — Data Analysis & Dashboard Ready | 5 | 2026-09-13 | SQL/EDA complete and 1-page Power BI dashboard built | In Progress
M5 — RAG Working | 7 | 2026-09-15 | Official documents retrieved with source-grounded answers | Done
M6 — AI Agent Working | 9 | 2026-09-17 | Agent routes between Data and RAG tools correctly | Done
M7 — Final Demo Ready | 10 | 2026-09-18 | Streamlit, evaluation, README, and GitHub complete | Done